## Setup
COMPONENT | STELLANTIS_EIP_COMAU_VERSA_TURNTABLE_SxxVTT
TYPE | VTT Drive
NAME | Sxx
DRIVE_NAME | Sxx
ENET_NODE | ENET_STAT_4thSYS_ID[126]
ENET_PORT | SxxESWy:17
SIO_ENABLE_OUTPUTS | Sxx_SIOy.O.baa/O.bbb
SIO_FEEDBACK_INPUT | Sxx_SIOy.I.bcc

## Pre-Validation
TRUE | 15 | 1 | FALSE | {TYPE} | {DRIVE_NAME} | Verify module name in I/O Configuration: {DRIVE_NAME}
FALSE | 15 | 1 | FALSE | {TYPE} | {NAME} | Verify ethernet node mapped tag: {ENET_NODE}
TRUE | 15 | 1 | FALSE | {TYPE} | {NAME} | Verify ethernet switch port connection: {ENET_PORT}
TRUE | 25 | 1 | FALSE | {TYPE} | {DRIVE_NAME} | Verify inputs are mapped to proper internal tag.
TRUE | 35 | 1 | FALSE | {TYPE} | {DRIVE_NAME} | Verify outputs are mapped to proper internal tag.
TRUE | 65 | 1 | FALSE | {TYPE} | {DRIVE_NAME} | Verify safety feedback input is mapped to {SIO_FEEDBACK_INPUT}.
TRUE | 65 | 1 | FALSE | {TYPE} | {DRIVE_NAME} | Verify safety enable outputs are mapped to {SIO_ENABLE_OUTPUTS}.

## Communications
TRUE | 15 | 1 | FALSE | {TYPE} | {DRIVE_NAME} | Verify communication status is ok.

## Safeties
TRUE | 115 | 5 | FALSE | {TYPE} | {DRIVE_NAME} | Verify drive is disabled when a gate or guard is not ok.
TRUE | 125 | 5 | FALSE | {TYPE} | {DRIVE_NAME} | Verify drive is enabled when cell is reset and all gates/guards are ok.

## Manual
TRUE | 15 | 10 | FALSE | {TYPE} | {DRIVE_NAME} | Verify manual operation and HMI indicators for turntable actions (move to position and jog).

## Dry Cycle
TRUE | 45 | 5 | FALSE | {TYPE} | {DRIVE_NAME} | Verify turntable drive is running in dry cycle.

## Automatic
TRUE | 45 | 5 | FALSE | {TYPE} | {DRIVE_NAME} | Verify turntable drive is running automatically.

## Diagnostics
TRUE | 15 | 1 | FALSE | {TYPE} | {DRIVE_NAME} | Verify correct message and indicators on HMI when drive disconnect is turned off.
TRUE | 55 | 1 | FALSE | {TYPE} | {DRIVE_NAME} | Verify correct message and indicators on HMI when drive ethernet is unplugged.
TRUE | 105 | 5 | FALSE | {TYPE} | {DRIVE_NAME} | Verify correct message and indicators on HMI when drive safety feedback is in wrong state ({SIO_FEEDBACK_INPUT}).